## Sheet1
Budget Dashboard (BUJI)
Job Number: J12345
Customer Name: ABC Corp.
Job Description: Custom Furniture Design
Start Date: April 13, 2025
Completion Date: August 30, 2025
Actual Direct Material Costs
Item Description | Measurement Unit |  | Quantity | Unit Cost | Total Cost
Bolt | Cubic yard |  | 10 | 200 | 2000
Steel | Unit |  | 150 | 50 | 7500
Drywall (sheets) | Sheets |  | 1000 | 10 | 10000
Roofing Materials | n/a |  | 400 | 10 | 4000
Flooring (sq. ft.) | Square feet |  | 7000 | 50 | 350000
|  |  |  | Total Direct Material Costs | 373500
Actual Direct Labor Costs
Name | Worker Role |  | Hours worked | Hourly Rate | Total Cost
Trishal | Project Manager |  | 8 | 75 | 600
Abhay | Site Supervisor |  | 10 | 50 | 500
Sushant | Electricians |  | 5 | 40 | 200
Purwanshu | Plumbers |  | 2 | 35 | 70
Khushi | General Labor |  | 10 | 25 | 250
Sahil | General Labor |  | 10 | 25 | 250
|  |  |  | Total Direct Labor Costs | 1620
Actual Direct Equipment Costs
Equipment Description | Quantity |  | Purchase/Lease cost | Maintenance cost | Total Cost
Excavator | 1 |  | 50000 | 5000 | 55000
Concrete Mixer | 2 |  | 25000 | 7000 | 32000
Cranes | 1 |  | 100000 | 10000 | 110000
Scaffolding | 15 |  | 15000 | 1500 | 16500
0
|  |  |  | Total Direct Equipment Costs | 213500
Actual Overhead Allocation
Overhead Type | Allocation Base | Value | Rate | Allocated Overhead
Office Expenses | Direct Labor | 80000 | 10% | 8000
Insurance | Project Value | 150000 | 5% | 7500
Utilities | Total Materials | 15000 | 2% | 300
Permits/Fees | Flat Rate | 7500 | 1 | 7500
|  |  | Total Overhead Cost | 23300
Planned vs. Actual Costs
Cost Category | Planned Costs |  | Cost Category | Actual Costs | Balance
Direct Material Costs | 300000 |  | Direct Material Costs | 373500 | -73500
Direct Labor Costs | 75000 |  | Direct Labor Costs | 1620 | 73380
Direct Equipment Costs | 209000 |  | Direct Equipment Costs | 213500 | -4500
Overhead Costs | 43470 |  | Overhead Costs | 23300 | 20170
Total Planned Costs | 627470 |  | Total Actual Costs | 611920 | 15550